Impact research of the ICA ToP methods in Kenya

- Proposed sites for research:

| Level | Site | County |
| --- | --- | --- |
| Full research: | Kabiro, Huruma, Kibra, etc. | Nairobi |
|  | Isinya | Kajiado |
|  | Kituoni | Kwale |
|  | Kamweleni | Machakos |
| Secondary research: | Serem | Vihiga |
|  | Vwevwesi | Kilifi |
|  | Hawinga | Siaya |

- Duration

The research team will have 5 days to prepare research to tools, 10 days fieldwork and 5 days of compiling, processing and documenting the impact research report.

- Research team by sites

| Research level | Site | Senior researcher | Assistant researcher |
| --- | --- | --- | --- |
| Full research | Kabiro | 1 | 2 |
|  | Huruma |  | 2 |
|  | Kituoni | 1 | 2 |
|  | Kamweleni | 1 | 2 |
|  | Isinya | 1 | 2 |
| Secondary research | Serem |  | 2 |
|  | Vwevwesi |  | 2 |
|  | Hawinga |  | 2 |

- Budget

  - Preparation

  - This will include preparation of research tools,

Printing and purchasing facilitation materials			Ksh.   50,000/=

  - Fieldwork per diem

- Out of station ksh. 6,000 (meals and lodging)

Full research

| No. | Site | Team | No. of days/daily allowance in Ksh. | Cost |
| --- | --- | --- | --- | --- |
|  | Coordinator for all sites | Consultant | 20 days x 8,000/= | 160,000/= |
|  | Kabiro and Huruma in Nairobi County | 1 Senior researcher and 4 Assistant researchers | 3days x 2 sites total 6 days X 5 researchers X 6,000/= | 180,000/= |
|  | Kituoni in Kwale County | 1 Senior researcher and 2 Assistant researchers | 3 days X 1 sites total 3 days X 3 researchers X 6,000/= | 54,000/= |
|  | Kamweleni in Machakos County | 1 Senior researcher and 2 Assistant researchers | 3 days X 1 sites total 3 days X 3 researchers X 6,000/= | 54,000/= |
|  | Isinya in Kajiado county | 1 Senior researcher and 2 Assistant researchers | 3 days X 1 site total 3 days X 3 researchers X 6,000/= | 54,000/= |
|  | Total |  |  | 502,000/= |

Secondary research

| No. | Site | Team | No. of days | Cost |
| --- | --- | --- | --- | --- |
|  | Serem in Vihiga county | 2 Assistant researchers | 2days x 1 sites total 2days X 2 researchers X 6,000/= | 24,000 /= |
|  | Vwevwesi in Kilifi County | 2 Assistant researchers | 2 days X 1 sites total 2 days X 2 researchers X 6,000/= | 24,000 /= |
|  | Hawinga in Siaya county | 2 Assistant researchers | 2 days X 1 sites total 2 days X 2 researchers X 6,000/= | 24,000 /= |
|  | Total |  |  | 72,000 /= |

  - Facilitations’ field work fees

| Researchers | Days / daily rate in Ksh. | Fees per day |
| --- | --- | --- |
| 1 team leader | 1 consultant X 20 days X 20,000/= | 400,000/= |
| 4 senior researchers | 4 senior researchers x 3 days x 10,000/= | 120,000/= |
| 10 assistant researchers | 10 assistant researchers x 3 days x 6,000/= | 180,000/= |
| Total |  | 700,000/= |

  - Distance travel

- Machakos, Kamweleni	1,000/= X 3		  3,000/=

- Kajiado, Isinya 		1,000/= X 2		  2,000/=

- Kilifi, Kituoni 		1,000/= X 3		  3,000/=

- Siaya, Hawinga		4,000/= X 2		 8,000/=

- Kakamega, Serem 		4,000/= X 2		 8,000/=

- Total					      Ksh. 24,000/=

  - Participants snacks

Snacks for focused group discussion:

- Kabiro		15 participants X 200/=	X 2 days	Ksh. 6,000

- Huruma		15 participants X 200/=	X 2 days	Ksh. 6,000

- Isinya		15 participants X 200/=	X 2 days	Ksh. 6,000

- Kituoni		15 participants X 200/=	X 2 days	Ksh. 6,000

- Kamweleni		15 participants X 200/=	X 2 days	Ksh. 6,000

Total 								Ksh.30,000

  - Contact persons

At least 2 contact persons on every site X 9 sites X 300/= X 3 days	Ksh. 16,200

  - Data collectors fees

At least 2 persons on every site X 6 sites X 1,500/= X 3 days		Ksh. 54,000

  - Grand total

- Preparation		Ksh.  50,000

- Fieldwork allowances	Ksh.574,000

- Transport 		Ksh.  18,000

- Consultancy fees 	Ksh.700,000

- Participants’ snacks	ksh.  30,000

- Contact persons	Ksh.  16,200

- Data collectors		Ksh.  54,000

- Total 			Ksh. 1,440,200 ($13,964) (£10,172.50)